## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 2- In Progress
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Sprint Backlog
L
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Foundations and Prerequistes for doing the project | 23rd Sep | 7th Oct | S.Srija | Gained insights about the fundamentals of python | Done |  | Introduction | Insallation of Python and Jupyter is done successfully | Learnt naming conventions and keywords | Explored the Data Types in python | Python Environment setup and revised variables | Practised examples related to datatypes in jupyter | Learnt loops and conditional statements | Learnt String operations and slicing | Worked on flow controls examples | Done problems using string methods and slicing | Revised Strings and began functions concept | Practised the functions concept | Revised all functions concepts and practised problems | Defined and called functions
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th Oct | 22nd Oct | S.Srija | Studied the project workflow, structure and data integration using Google sheets | In Progress |  | Learnt OOPS Concepts | Learnt the packages concept in python | Learnt NLP , NLTK and text wrangling ,cleaning concepts | Understood NLTK library and spaCy library concepts | Practised the NLTK library tools and spacy | Introduction and basics about the Project | Gave explanation about the project | Created and activated virtual environment in VS Code | Understood concepts about Hugging Face transformers | Interactive session about project | Revised and practiced Hugging face Transformers | Revised the previous concepts | Practised the NLP , nltk library | Google Sheet Intergration is done
3 |  | Social Media Integration, Content Creation, Optimization | 23rd Oct | 6th Nov | S.Srija | Gained practical experience in social media API integration and content generation | Done |  | Learnt API Integration with twitter | In detail About API integration with twitter | Worked on Facebook API integration | Working on Instagram and linkedin API integration | Interactive session on API integrations | Revised API Integration | Intro about Mock data generation | Content Generation using LLM and groq API | Learnt about googlesheet connector | Introduction about the LLM | Practiced LLM fundamentals | Interactive Session | Understood how to generate variations of content | Practiced to generate the content with different variations
4 |  | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | S Srija | Learnt about sentiment analysis, slack integration and deployment on streamlit | Done |  | Understood about API and stages of it | Learnt the concept of API in detail | Revised and practiced API concepts | Worked in the Assignment given | Interactive session | Understand about content optimization | Understood sentiment analysis concept | Learnt Slack integration | Understood about A/B testing concept | Revised A/B testing concepts | Revised Sentiment Analysis | Understood the Project Workflow | Discussion about mock presentation | Mock Presentation
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7